## MEO - Engineering
MUNICIPALITY OF PINAMALAYAN
Province of Oriental Mindoro
ANNUAL AGENCY PERFORMANCE APPRAISAL
AAPA MATRIX 1: STATE OF OFFICE PERFORMANCE ASSESSMENT PY 2025
MATRIX 1A: STATUS OF PHYSICAL AND FINANCIAL PERFORMANCE OF PROGRAMS/PROJECTS/ACTIVITIES AS PER APPROVED 2025 AIP/AB AND 2025 SIPs/SBs MATRIX 1B: STATUS OF FINANCIAL PERFORMANCE OF OFFICE CURRENT OPERATING EXPENSES MATRIX 1C: DEVELOPMENT OBJECTIVES BASED ON OFFICE MANDATE AS PER MTDP 2023-2025 (PY 2025) MATRIX 1D: PERFORMANCE MANAGEMENT BASED ON PERFORMANCE STANDARD GUIDE (COMMITMENT TARGET AGAINST ACTUAL ACCOMPLISHMENT)
AS OF DECEMBER 31, 2025
SECTOR: |  | Infrastructure
DEPARTMENT/OFFICE: |  | MEO - Engineering
MAJOR FINAL OUTPUT: |  | Roads and bridges
ORGANIZATIONAL OUTCOME: |  | Improved access
MATRIX 1C: DEVELOPMENT OBJECTIVES AS PER OFFICE MANDATE AS PER MTDP 2023-2025 (PY 2025)
Results | Performance Indicators | Target for Indicators PY 2025 | Actual Accomplishment | Issues/Concerns/Gaps | Recommendation / Intervention
-1 | -2 | -3 | -4 | -5 | -6
Improved road network | Km of road concreted | 12 | 9 | 75% of target accomplished (Partially accomplished). Gap of 3 against the target of 12. Concerns reported: Failed bidding for two projects and delayed release of funds; backhoe under repair. Main factors: Funding / Budget, Equipment / Logistics, Delays / Procurement. | (1) Prioritize the activity in the next AIP/budget cycle and identify supplemental or alternative funding (e.g. Supplemental Budget, 20% Development Fund, grants). (2) Procure, repair or schedule preventive maintenance of equipment and vehicles; ensure supplies are stocked ahead of time. (3) Address the delays: start procurement and approvals early (align with the Annual Procurement Plan), monitor milestones monthly and resolve bottlenecks with the offices concerned (e.g. BAC/GSO, approving authorities).
| Bridges repaired | 4 | 4 | 100% of target accomplished (Fully accomplished). No issues or concerns reported. | Sustain the performance and consider a higher target in the next planning cycle.
Safe public buildings | Buildings inspected | 200 | 60 | 30% of target accomplished (Not accomplished / Critical). Gap of 140 against the target of 200. Concerns reported: Kulang ang tao at walang sasakyan para sa inspection. Main factors: Manpower / Staffing, Equipment / Logistics. | (1) Priority attention: prepare a recovery plan with monthly monitoring by the Department Head. (2) Fill vacant positions or augment through job order/COS personnel; redistribute workload and cross-train staff. (3) Procure, repair or schedule preventive maintenance of equipment and vehicles; ensure supplies are stocked ahead of time.
| Permits issued within 3 days | 100% | 92% | 92% of target accomplished (Substantially accomplished). Gap of 8 against the target of 100. Concerns reported: Slow internet and encoding delays. Main factors: Delays / Procurement, Technology / Data. | (1) Address the delays: start procurement and approvals early (align with the Annual Procurement Plan), monitor milestones monthly and resolve bottlenecks with the offices concerned (e.g. BAC/GSO, approving authorities). (2) Upgrade systems and connectivity, standardize data/records management and train users on the tools.
Result 0 | Indicator 0 | 10 | 0 | 0% of target accomplished (Not accomplished / Critical). Gap of 10 against the target of 10. Concerns reported: Typhoon damage and lack of funds Main factors: Funding / Budget, Weather / Calamity. | (1) Priority attention: prepare a recovery plan with monthly monitoring by the Department Head. (2) Prioritize the activity in the next AIP/budget cycle and identify supplemental or alternative funding (e.g. Supplemental Budget, 20% Development Fund, grants). (3) Build contingency schedules for weather and calamity risks; coordinate with MDRRMO and re-program affected activities.
Result 1 | Indicator 1 | 10 | 1 | 10% of target accomplished (Not accomplished / Critical). Gap of 9 against the target of 10. Concerns reported: Typhoon damage and lack of funds Main factors: Funding / Budget, Weather / Calamity. | (1) Priority attention: prepare a recovery plan with monthly monitoring by the Department Head. (2) Prioritize the activity in the next AIP/budget cycle and identify supplemental or alternative funding (e.g. Supplemental Budget, 20% Development Fund, grants). (3) Build contingency schedules for weather and calamity risks; coordinate with MDRRMO and re-program affected activities.
Result 2 | Indicator 2 | 10 | 2 | 20% of target accomplished (Not accomplished / Critical). Gap of 8 against the target of 10. Concerns reported: Typhoon damage and lack of funds Main factors: Funding / Budget, Weather / Calamity. | (1) Priority attention: prepare a recovery plan with monthly monitoring by the Department Head. (2) Prioritize the activity in the next AIP/budget cycle and identify supplemental or alternative funding (e.g. Supplemental Budget, 20% Development Fund, grants). (3) Build contingency schedules for weather and calamity risks; coordinate with MDRRMO and re-program affected activities.
Result 3 | Indicator 3 | 10 | 3 | 30% of target accomplished (Not accomplished / Critical). Gap of 7 against the target of 10. Concerns reported: Typhoon damage and lack of funds Main factors: Funding / Budget, Weather / Calamity. | (1) Priority attention: prepare a recovery plan with monthly monitoring by the Department Head. (2) Prioritize the activity in the next AIP/budget cycle and identify supplemental or alternative funding (e.g. Supplemental Budget, 20% Development Fund, grants). (3) Build contingency schedules for weather and calamity risks; coordinate with MDRRMO and re-program affected activities.
Result 4 | Indicator 4 | 10 | 4 | 40% of target accomplished (Not accomplished / Critical). Gap of 6 against the target of 10. Concerns reported: Typhoon damage and lack of funds Main factors: Funding / Budget, Weather / Calamity. | (1) Priority attention: prepare a recovery plan with monthly monitoring by the Department Head. (2) Prioritize the activity in the next AIP/budget cycle and identify supplemental or alternative funding (e.g. Supplemental Budget, 20% Development Fund, grants). (3) Build contingency schedules for weather and calamity risks; coordinate with MDRRMO and re-program affected activities.
Result 5 | Indicator 5 | 10 | 5 | 50% of target accomplished (Partially accomplished). Gap of 5 against the target of 10. Concerns reported: Typhoon damage and lack of funds Main factors: Funding / Budget, Weather / Calamity. | (1) Prioritize the activity in the next AIP/budget cycle and identify supplemental or alternative funding (e.g. Supplemental Budget, 20% Development Fund, grants). (2) Build contingency schedules for weather and calamity risks; coordinate with MDRRMO and re-program affected activities.
Result 6 | Indicator 6 | 10 | 6 | 60% of target accomplished (Partially accomplished). Gap of 4 against the target of 10. Concerns reported: Typhoon damage and lack of funds Main factors: Funding / Budget, Weather / Calamity. | (1) Prioritize the activity in the next AIP/budget cycle and identify supplemental or alternative funding (e.g. Supplemental Budget, 20% Development Fund, grants). (2) Build contingency schedules for weather and calamity risks; coordinate with MDRRMO and re-program affected activities.
Result 7 | Indicator 7 | 10 | 7 | 70% of target accomplished (Partially accomplished). Gap of 3 against the target of 10. Concerns reported: Typhoon damage and lack of funds Main factors: Funding / Budget, Weather / Calamity. | (1) Prioritize the activity in the next AIP/budget cycle and identify supplemental or alternative funding (e.g. Supplemental Budget, 20% Development Fund, grants). (2) Build contingency schedules for weather and calamity risks; coordinate with MDRRMO and re-program affected activities.
Result 8 | Indicator 8 | 10 | 8 | 80% of target accomplished (Substantially accomplished). Gap of 2 against the target of 10. Concerns reported: Typhoon damage and lack of funds Main factors: Funding / Budget, Weather / Calamity. | (1) Prioritize the activity in the next AIP/budget cycle and identify supplemental or alternative funding (e.g. Supplemental Budget, 20% Development Fund, grants). (2) Build contingency schedules for weather and calamity risks; coordinate with MDRRMO and re-program affected activities.
Result 9 | Indicator 9 | 10 | 9 | 90% of target accomplished (Substantially accomplished). Gap of 1 against the target of 10. Concerns reported: Typhoon damage and lack of funds Main factors: Funding / Budget, Weather / Calamity. | (1) Prioritize the activity in the next AIP/budget cycle and identify supplemental or alternative funding (e.g. Supplemental Budget, 20% Development Fund, grants). (2) Build contingency schedules for weather and calamity risks; coordinate with MDRRMO and re-program affected activities.
Result 10 | Indicator 10 | 10 | 10 | 100% of target accomplished (Fully accomplished). Concerns reported: Typhoon damage and lack of funds Main factors: Funding / Budget, Weather / Calamity. | (1) Prioritize the activity in the next AIP/budget cycle and identify supplemental or alternative funding (e.g. Supplemental Budget, 20% Development Fund, grants). (2) Build contingency schedules for weather and calamity risks; coordinate with MDRRMO and re-program affected activities. (3) Sustain the performance and consider a higher target in the next planning cycle.
NOTE:
Please refer to Medium-Term Development Plan (MTDP) 2023-2025 for guidance

## MHO
MUNICIPALITY OF PINAMALAYAN
Province of Oriental Mindoro
ANNUAL AGENCY PERFORMANCE APPRAISAL
AAPA MATRIX 1: STATE OF OFFICE PERFORMANCE ASSESSMENT PY 2025
MATRIX 1A: STATUS OF PHYSICAL AND FINANCIAL PERFORMANCE OF PROGRAMS/PROJECTS/ACTIVITIES AS PER APPROVED 2025 AIP/AB AND 2025 SIPs/SBs MATRIX 1B: STATUS OF FINANCIAL PERFORMANCE OF OFFICE CURRENT OPERATING EXPENSES MATRIX 1C: DEVELOPMENT OBJECTIVES BASED ON OFFICE MANDATE AS PER MTDP 2023-2025 (PY 2025) MATRIX 1D: PERFORMANCE MANAGEMENT BASED ON PERFORMANCE STANDARD GUIDE (COMMITMENT TARGET AGAINST ACTUAL ACCOMPLISHMENT)
AS OF DECEMBER 31, 2025
SECTOR: |  | Social
DEPARTMENT/OFFICE: |  | MHO
MAJOR FINAL OUTPUT: |  | Roads and bridges
ORGANIZATIONAL OUTCOME: |  | Improved access
MATRIX 1C: DEVELOPMENT OBJECTIVES AS PER OFFICE MANDATE AS PER MTDP 2023-2025 (PY 2025)
Results | Performance Indicators | Target for Indicators PY 2025 | Actual Accomplishment | Issues/Concerns/Gaps | Recommendation / Intervention
-1 | -2 | -3 | -4 | -5 | -6
Healthier residents | Children immunized | 500 | 520 | 104% of target accomplished (Fully accomplished). Target was exceeded. No issues or concerns reported. | Sustain the performance and consider a higher target in the next planning cycle.
| Health workers trained | 30 | 10 | 33.3% of target accomplished (Not accomplished / Critical). Gap of 20 against the target of 30. Concerns reported: Limited funds; poor attendance of barangay health workers. Main factors: Funding / Budget, Coordination / Stakeholders. | (1) Priority attention: prepare a recovery plan with monthly monitoring by the Department Head. (2) Prioritize the activity in the next AIP/budget cycle and identify supplemental or alternative funding (e.g. Supplemental Budget, 20% Development Fund, grants). (3) Strengthen coordination with partner offices, barangays and agencies through regular meetings and clear MOAs.
NOTE:
Please refer to Medium-Term Development Plan (MTDP) 2023-2025 for guidance